## Slide 1
ITEL AFFILIATED COLLEGES
South-Based Colleges — Partnership Status Dashboard
11
Total Colleges
2
MoU Signed
3
MoU In Progress
6
Planned / Upcoming
1
Initial Contact
1
Active
STATUS BREAKDOWN
MoU Signed (2)
MoU In Progress (3)
Planned / Upcoming (6)
Active / Initial (2)

## Slide 2
ITEL AFFILIATED — COLLEGE STATUS TRACKER
# | College Name | Current Status | Next Steps | Stage
1 | SRM-AP University | Activity of Club Picking up (March 13th last meeting held with Faculty SPOC). Robotics Workshop Proposal shared. | Follow the template followed at West Bengal Colleges. Checklist & Member IDs. | Active
2 | SSN-CE | Launch Workshop – Next Semester | Customised plan with activity of existing club to be ramped up and to create pipeline of pre-incubatees. | Planned
3 | IIIT-H | Launch Workshop – Next Semester (July–August) | — | Planned
4 | Presidency University | Tentatively to be launched in July | Awaiting Dates from them. Meeting with Core Students team to be done. | Planned
5 | Karunya | Awaiting Dates from them. | Meeting with Core Students team to be done. | Planned
6 | MAMCET | Meeting with Core Students team Faculty done. | Launch Dates to be finalised. To Share docs & Action items for Core team. | Planned
7 | Crescent | MoU Signed and shared to them on 23rd March | Meeting with Core Team and Faculty-in Charge requested. Needs follow-up. | MoU Signed
8 | Atria University | MoU Signed and shared to them on 21st March | Meeting with Faculty SPOC requested. Did a follow up on April 25th. | MoU Signed
9 | Avinashilingam | MoU formalities in progress. Kickstart Projects list shared. | Meeting with Core Students team & Faculty-in Charge done on April 16th. | MoU in Progress
10 | PSNA | MoU formalities in progress. Kickstart Projects list shared. | Meeting with Core Students team & Faculty-in Charge to be done. Very Slow Response. Faculty in-charge makes calls out of the blue. | MoU in Progress
11 | Chennai Institute of Technology | First meeting with Director – Innovation & faculty incharge on April 25th | — | Initial Contact

## Slide 3
COLLEGE PIPELINE — STAGE VIEW
Initial Contact
Chennai Institute of Technology
Planned / Upcoming
SSN-CE
IIIT-H
Presidency University
Karunya
MAMCET
MoU in Progress
Avinashilingam
PSNA
MoU Signed
Crescent
Atria University
Each column represents a stage in the college onboarding pipeline.